## REQUIREMENTS
#VALUE!
Expert in Teams (EXT25)
Project Name :
Date : | 2026-05-31
Project Requirements
REQUIREMENT LIST |  |  |  |  | REQUIREMENTS ANALYSIS
ID | REQUIREMENT DESCRIPTION | CATEGORY | PRIORITY | ACCEPTANCE CRITERIA | COMPLEXITY | IN SCOPE? | TEST OR VERIFICATION | REQUIREMENT DELIVERY
Give each requirement a unique ID. | The feature, function, condition or capability that is required from the project. | The category or grouping of the requirement. Example: functional, technical, operational, KPI (result metric), transitional. | The priority of the requirement. Example: P1, P2, P3 or MoSCoW (Must have, should have, could have, won't have). | The criteria that the requirement must have for it to be accepted by the Company & SDU Team | An indication of how complex it will be to deliver the requirement. Example: High, Medium, Low or Very Simple, Simple, hard, not possible, not possible now. | Whether the requirement is going to be in the scope of the project. This will be agreed by the Company & SDU Team. | How the requirement will be checked and tested. For example, it can be based on a performance metric | The project phase or date when the requirement will be delivered (Can be connected to the Gantt chart)
FR-001 | Capture a product label image using the device camera. | Functional | Must | User can open capture view and take a photo; image is stored in app storage and linked to a new attempt; user is taken to extraction/processing. | Medium | Yes | Manual acceptance test on iOS and Android using real labels; verify image file exists and attempt is created. | Sprint 2
FR-002 | Import a product label image from gallery/files. | Functional | Must | User can select an existing image; image is copied into app storage and linked to a new attempt; extraction/processing starts. | Low | Yes | Manual test on iOS/Android/Web using sample images; verify attempt creation. | Sprint 2
FR-003 | Support multi-image capture/import for a single item (split labels). | Functional | Should | User can attach 2+ images to one attempt; extraction uses all images; confirmation screen shows a single merged result with traceability to the source images. | Medium | Yes | Manual test with two images that contain complementary fields; verify merged output contains fields from both. | Sprint 3
FR-004 | Persist captured/imported images locally and associate them with attempts. | Functional | Must | Each attempt retains its image(s) across app restarts until deleted by retention rules or user action; storage path is app-private. | Medium | Yes | Restart app and verify attempt still shows the image thumbnail and can re-open images. | Sprint 2
FR-005 | Preprocess images before extraction (orientation, resize, basic contrast improvements). | Technical | Should | Preprocessed image(s) are used for extraction; preprocessing never removes readable content (no cropping that loses text); preprocessing can be disabled for troubleshooting. | Medium | Yes | Visual inspection on a small test set; A/B compare extraction accuracy with/without preprocessing on glare/angle samples. | Sprint 2; improved in Sprint 6
FR-006 | Decode barcode(s) present on label images. | Functional | Must | For images containing a supported barcode, the app returns the decoded value and symbology; if no barcode is present, extraction continues without failure. | Medium | Yes | Test with sample EAN/UPC/Code128 labels; verify decoded value matches ground truth. | Sprint 2
FR-007 | Include decoded barcode values as supplemental data and map them to relevant fields (e.g., EAN/UPC) when applicable. | Functional | Must | Decoded barcode values are stored in the attempt record; if the target schema includes `ean_or_upc`, it is populated from a matching barcode when available; raw barcode list remains available. | Medium | Yes | Integration test on a dataset with known EAN/UPC; verify both mapped field and raw list are present. | Sprint 2
FR-008 | Extract structured data from label images using a schema-driven vision-language (VL) provider (VL-first). | Functional | Must | Given 1+ label images, the provider returns a JSON payload conforming to the internal extraction schema; extraction completes without requiring a separate OCR-only stage. | High | Yes | Provider integration tests using fixed images; validate output JSON against schema. | Sprint 2
FR-009 | Prevent unsupported field inference by limiting what the model is asked to fill and requiring “unknown” for missing evidence. | Technical | Must | Prompts/request schema exclude manual-only fields (e.g., condition); provider instructions require leaving fields blank/null when not explicitly present; confirmations show blanks rather than hallucinated values on labels missing the field. | Medium | Yes | Regression test set where certain fields are absent; verify fields remain empty/null pre-review. | Sprint 3
FR-010 | Validate provider output against a versioned JSON schema and apply normalization rules. | Technical | Must | Output includes `schema_version`; runtime validation rejects non-JSON or schema-invalid output; normalization rules are applied (e.g., trim, collapse whitespace; case-insensitive comparisons for evaluation). | Medium | Yes | Unit tests for schema validation and normalization; negative tests for invalid JSON. | Sprint 3
FR-011 | Capture and surface confidence/uncertainty when available. | Functional | Should | If provider supplies per-field confidence, it is stored and shown; if not available, fields are still validated and visually flagged when missing/invalid. | Medium | Yes | Manual test with a provider that returns confidence; verify UI highlights low-confidence fields and allows edits. | Sprint 6
FR-012 | Provide a mandatory confirmation and editing screen prior to submission/export. | Functional | Must | User cannot submit/export without visiting the confirmation screen; invalid/missing required fields are clearly indicated; edited values are used as the final payload. | Medium | Yes | Manual acceptance test: attempt submission is blocked until confirmation; edited value persists in payload. | Sprint 3
FR-013 | Provide dropdown/autocomplete for previously entered values (e.g., Manufacturer) on the confirmation screen. | Functional | Should | Confirmation inputs can suggest previous values from attempt history; selecting a suggestion fills the field; user can still type a new value. | Low | Yes | Manual test: enter manufacturer on attempt A; on attempt B, manufacturer suggestion appears and can be selected. | Sprint 3
FR-014 | Support manual entry of additional registration fields (e.g., item category and condition) and corrections of extracted fields. | Functional | Must | User can enter/override values for all required registration fields; system records whether a field was extracted vs manually set; manual-only fields are never auto-filled by the model. | Medium | Yes | Manual test: set condition and category; verify stored as `source=manual` (or equivalent) and included in submission/export. | Sprint 3
FR-015 | Maintain a mapping layer from internal extraction schema to partner-company registration fields and formats. | Technical | Must | Internal schema remains stable while mapping rules produce an ingestion payload using partner field names/formats; mapping rules are versioned and testable. | High | Yes | Unit tests for mapping rules; acceptance test by posting mapped payload to mock endpoint or validating export file format. | Sprint 1, refined through Sprint 5
FR-016 | Provide configurable provider settings (provider type, endpoint/base URL, model ID). | Functional | Must | User can configure and persist provider settings; extraction uses the configured provider on next run; provider ID/model ID recorded in metadata. | Medium | Yes | Manual test: change provider settings and confirm subsequent extraction uses new provider/model (via metadata). | Sprint 4
FR-017 | Support Bring Your Own Key (BYOK) for remote providers. | Functional | Must | User can enter provider API key/token in Settings; key is required before remote extraction can run; key can be removed/rotated by the user. | Medium | Yes | Manual test: run extraction without key (blocked); add key (succeeds); remove key (blocked). | Sprint 4
FR-018 | Store secrets securely using OS secure storage where supported. | Security | Must | On iOS/Android, secrets are stored via secure storage (Keychain/Keystore); secrets are never written to logs or exported; web/desktop mode shows a warning if secure storage is not available and does not persist secrets by default. | Medium | Yes | Security review + manual inspection (no secrets in local files/logs); platform test on iOS/Android with secure storage APIs. | Sprint 4
FR-019 | Implement provider fallback routing when the primary extraction provider fails. | Functional | Should | If primary provider times out/returns invalid output, the app retries with a configured fallback provider; user is informed which provider succeeded/failed. | High | Yes | Integration test with a forced failure in primary provider; verify fallback succeeds and metadata records provider used. | Sprint 4
FR-020 | Allow users to retry extraction and/or retake images for an attempt. | Functional | Should | User can retry extraction without re-capturing; user can replace an image and re-run extraction; retry count is recorded for the attempt. | Low | Yes | Manual test: retry increments counter; retake image changes image hash and affects extraction. | Sprint 3
FR-021 | Provide configurable ingestion settings (endpoint URL and authentication mode). | Functional | Must | Settings support configuring a POST endpoint URL; supports no-auth and bearer-token auth at minimum; settings persist across restarts. | Medium | Yes | Manual test: configure endpoint and send; verify correct URL and headers. | Sprint 5
FR-022 | Submit confirmed payload via HTTP POST ingestion. | Functional | Must | App sends `POST` with `application/json`; any 2xx response marks attempt as `sent`; non-2xx response records error and leaves attempt queued/unsent. | Medium | Yes | Integration test against mock endpoint returning 2xx and 4xx/5xx; verify status transitions. | Sprint 5
FR-023 | Provide an offline submission queue that stores unsent payloads for later retry. | Functional | Must | If offline or ingestion fails, payload is queued; user can trigger resend (manual or automatic) when back online; queue supports multiple pending items. | High | Yes | Manual test by disabling network; submit; re-enable; resend and verify successful POST. | Sprint 5
FR-024 | Ensure the offline queue persists across app restarts. | Functional | Must | Queued payloads remain queued after force close and reopen; queued items are not duplicated; successful sends are removed from the queue. | High | Yes | Reliability test: queue items, force close app 10+ times, verify queue integrity and eventual sending. | Sprint 5
FR-025 | Maintain and display a history of the last 20 attempts with status and details. | Functional | Must | History lists attempts with timestamp and status (e.g., processing, needs review, queued, sent, failed); user can open an attempt to view images, extracted JSON, mapped payload, and errors. | Medium | Yes | Manual test: create >20 attempts and confirm only the latest 20 remain; verify detail view is accessible. | Sprint 3
FR-026 | Enforce retention and deletion rules for attempts. | Operational | Must | The system retains exactly the last 20 attempts and deletes older ones (including related images/payloads); user can manually delete an attempt and optionally clear all local data. | Medium | Yes | Create 21 attempts and verify attempt #1 is deleted; confirm storage usage drops accordingly. | Sprint 3
FR-027 | Support export of confirmed data as JSON and CSV as an integration fallback. | Functional | Must | User can export a confirmed attempt (or batch) to JSON and CSV; exported files match the defined field list and mapping rules; export includes schema version and metadata where applicable. | Medium | Yes | Compare exported files to expected contract format; import test using partner-provided sample importer (if available). | Sprint 5
FR-028 | Provide a local mock ingestion server that simulates the production POST endpoint. | Transitional | Must | Mock server accepts ingestion payload and returns configurable responses (2xx/4xx/5xx); used for development and acceptance testing when partner endpoint is unavailable. | Medium | Yes | Run mock server locally and execute end-to-end submission from the app; verify stored request payloads. | Sprint 5
FR-029 | Record traceability metadata per attempt (timestamp, provider/model IDs, image hash). | Technical | Should | Each attempt stores capture time and a stable identifier (e.g., SHA-256 hash) for each image; provider/model identifiers are stored for audit and evaluation. | Low | Yes | Unit test for hash function; verify metadata is present in stored attempt data. | Sprint 3
FR-030 | Define the minimum target field set to extract and register. | Functional | Must | The internal schema and UI support at minimum: manufacturer, model/type or product number, serial number (when present), country of origin (when present), SKU, product text/description, and EAN/UPC (when present); additional fields (item category, condition) are supported for manual entry. | Medium | Yes | Field checklist review with partner + manual tests on representative labels; verify schema/UI contain these fields. | Sprint 1
NFR-001 | Run on iOS and Android, and provide a usable desktop experience via web (responsive layout). | Technical | Must | Core workflow (capture/import, confirmation/edit, submission/export, history, settings) functions on iOS and Android; web build works in a modern desktop browser for non-camera flows (at minimum import). | High | Yes | Cross-platform test matrix; verify web build import/extraction/confirmation works. | Sprint 2-7, acceptance in Sprint 7
NFR-002 | Remote extraction performance. | KPI | Must | Over a 50 Mbps connection, the confirmation screen is reached within 6.0 seconds for at least 90% of attempts on the reference device. | Medium | Yes | Performance measurement on a fixed image set; report p50/p90 timings. | Sprint 7
NFR-003 | User interface responsiveness. | Non-functional | Must | UI responds to user input within 100 ms for >99% of interactions on the reference device. | Medium | Yes | Manual profiling and instrumentation during UI tests; document results. | Sprint 7
NFR-004 | Cold start time. | Non-functional | Should | Cold start to an operable capture/import screen in < 3.0 seconds on the reference device. | Medium | Yes | Timed cold-start measurements across 10 runs; report median. | Sprint 7
NFR-005 | Offline queue reliability. | Non-functional | Must | Offline queue survives 100% of forced app restarts during a test sequence with pending items. | Medium | Yes | Reliability test script/manual procedure; record pass/fail. | Sprint 5 build; validated in Sprint 7
NFR-006 | Transport security for remote communications. | Security | Must | All remote calls (providers and ingestion) use HTTPS with TLS 1.2+; app rejects non-HTTPS endpoints by default (or requires explicit override with warning). | Medium | Yes | Config validation tests; manual inspection of network traffic in dev mode. | Sprint 4-5
NFR-007 | Data minimization and storage limits per attempt. | Operational | Should | Stored data per attempt (images + JSON + metadata) is kept <= 10 MB on average; large images are resized/compressed to meet this limit without losing readability. | Medium | Yes | Measure storage usage on a sample of attempts; report average and max. | Sprint 6
NFR-008 | Attempt retention limit. | Operational | Must | The app retains exactly the latest 20 attempts and removes older attempts automatically (including files). | Low | Yes | Create 25 attempts and confirm only 20 remain; confirm oldest entries are deleted. | Sprint 3
NFR-009 | End-to-end workflow reliability under stable network conditions. | Non-functional | Must | With stable connectivity, >=95% of attempts complete capture/import -> extraction -> confirmation -> submission without requiring an app restart; failures provide a recovery path (retry, fallback, or queue). | Medium | Yes | Reliability run on a fixed image set with stable network; record completion rate and failure causes. | Sprint 7
NFR-010 | Business-sensitive data handling. | Security | Must | Label images and extracted data are treated as business-sensitive: stored app-private; transmitted only to configured provider(s) and ingestion endpoint; no analytics/telemetry that includes images or extracted fields; users can clear local data. | Medium | Yes | Code/config review + manual test: verify no unexpected network calls and that “clear data” removes local attempts. | Sprint 4-7
KPI-001 | Pre-review extraction accuracy on a held-out dataset. | KPI | Must | For mandatory fields (manufacturer, model/type, serial number, country of origin), achieve >=85% correct pre-review extraction on an agreed held-out set, after normalization rules; report per-field accuracy. | High | Yes | Evaluation harness run on held-out set; publish results table and methodology. | Sprint 6-7
KPI-002 | Registration time reduction compared to manual entry. | KPI | Should | Demonstrate >=50% reduction in median registration time per item using the tool (including confirmation/editing) vs manual entry on the same label set; report median and IQR. | High | Yes | Time study protocol execution; statistical summary in evaluation package. | Sprint 6-7
KPI-003 | Dataset size and split for evaluation. | KPI | Must | Collect >=50 real label images with diverse manufacturers/layouts and capture conditions; split 60% dev and 40% held-out; freeze held-out set for final testing. | Medium | Yes | Dataset inventory file + audit of counts; store split definition and freeze date. | Sprint 1 plan; collection through Sprint 6
KPI-004 | Ground truth quality for evaluation. | KPI | Should | Ground truth transcriptions are created for all evaluation images; a second team member cross-checks a sample and discrepancies are resolved and documented. | Medium | Yes | Review log + spot-check report; inter-annotator discrepancy notes. | Sprint 6
DOC-001 | Deliver D1: partner-approved field list, internal schema, and ingestion/export contract (incl. mapping rules). | Transitional | Must | Field list and formats are reviewed with partner; schema is versioned; ingestion contract specifies endpoint/auth/payload; mapping rules documented. | Medium | Yes | Document review session with partner; mock endpoint accepts payload matching the contract. | Sprint 1 and Sprint 5 finalization
DOC-002 | Deliver D2: functional prototype implementing the end-to-end workflow. | Transitional | Must | Prototype supports capture/import, extraction, confirmation/edit, submission/queueing, settings, and history on iOS/Android; demo flow reproducible. | High | Yes | End-to-end demo run using representative labels; acceptance checklist signed by team. | Sprint 5
DOC-003 | Deliver D3: evaluation package (dataset description, methodology, and results). | Transitional | Must | Package includes dataset description, ground truth procedure, per-field accuracy, end-to-end success rate, and time-savings results. | Medium | Yes | Re-run evaluation from documented steps and reproduce results. | Sprint 7
DOC-004 | Deliver D4: technical documentation (install, configuration, security model, troubleshooting). | Transitional | Must | A new developer can install and run the prototype; configuration steps for providers/ingestion are documented; security assumptions and limitations are stated. | Low | Yes | Documentation walkthrough by a team member not authoring the doc; fix identified gaps. | Sprint 8
DOC-005 | Deliver D5: final demo and handover package. | Transitional | Must | Includes demo script, known limitations, and a prioritized backlog for future work; final presentation materials prepared. | Low | Yes | Dry-run demo and presentation; verify handover artifacts are complete. | Sprint 8
D-001 | Local vision-language (VL) extraction mode (on-device). | Technical | Could | A supported device can run extraction without network access; output remains schema-valid; user can switch between local and remote extraction. | High | Yes (time permitting) | Benchmark on-device extraction on a small test set; compare accuracy/latency vs remote. | Sprint 6-8
D-002 | Provider benchmarking and comparison tooling. | KPI | Could | Tooling can run the same dataset through multiple providers/models and produce comparable metrics (accuracy, latency, cost notes). | Medium | Yes (time permitting) | Repeatable benchmark run documented; results table produced. | Sprint 6-7
D-003 | Confidence-focused user interface enhancements. | UX | Could | Confirmation UI clearly highlights low-confidence fields (where available) and missing/invalid fields; user can filter/jump to fields needing attention. | Medium | Yes (time permitting) | Usability walkthrough on a test set; measure time-to-correct vs baseline UI. | Sprint 6-7
D-004 | Image/keyword search helper for manufacturer or product info (agentic/assisted lookup). | Functional | Could | User can search by image or keywords to retrieve reference info (e.g., manufacturer name normalization); any retrieved data is explicitly marked as “suggested” and requires user confirmation. | High | Yes (time permitting) | Demo with controlled examples; verify suggested values never auto-submit without confirmation. | Sprint 7-8
D-005 | Support additional local VL models for image-to-JSON extraction. | Technical | Could | App can download/select at least one additional local model and run extraction with the same schema; model selection is exposed in Settings. | High | Yes (time permitting) | Manual test on supported devices; verify schema validation passes across models. | Sprint 7-8
CON-001 | Do not train custom vision models on proprietary company data. | Constraint | Must | No custom training pipeline or trained proprietary model artifacts are produced; solution uses existing local/remote models only. | Low | Yes | Architecture/code review; confirm evaluation uses off-the-shelf models. | Throughout
CON-002 | Do not implement full integration into the partner’s internal UI; deliver ingestion contract + adapter/export instead. | Constraint | Must | No changes are required in the partner UI to test the prototype; integration is demonstrated via configurable HTTP ingestion and/or export files. | Low | Yes | Acceptance test using mock endpoint and export files; partner review of contract. | Sprint 5
CON-003 | Do not infer fields that are not present on the label (e.g., condition) beyond user entry. | Constraint | Must | Extracted outputs do not include invented values for non-label fields; such fields remain empty until user provides them. | Medium | Yes | Regression tests with missing fields; manual spot checks on evaluation set. | Sprint 3
CON-004 | Do not target large-scale production deployment or enterprise device management. | Constraint | Won't | Deliverable is a functional prototype and evaluation; no MDM, SSO, or production rollout plan beyond a handover backlog. | Low | Yes | Review deliverables vs scope boundaries. | Sprint 8

## DEFINITIONS
DEFINITIONS
REQUIREMENT ID
Give each requirement a unique ID.
This Takes You to Requirement ID in the Template
REQUIREMENT DESCRIPTION
The feature, function, condition or capability that is required from the project.
This Link Takes You to Requirement Description in the Template
REQUESTED BY
The stakeholder who requested the requirement.
This Link Takes You to Requested By in the Template
CATEGORY
The category or grouping of the requirement. Example: functional, technical, operational, KPI (result metric), transitional.
This Link Takes You to Category in the Template
PRIORITY
The priority of the requirement. Example: P1, P2, P3 or MoSCoW (Must have, should have, could have, won't have).
This Link Takes You to Priority in the Template
ACCEPTANCE CRITERIA
The criteria that the requirement must have for it to be accepted by the Company & SDU Team
This Link Takes You to Acceptance Criteria in the Template
COMPLEXITY
An indication of how complex it will be to deliver the requirement. Example: High, Medium, Low or Very Simple, Simple, hard, not possible, not possible now.
This Link Takes You to Complexity in the Template
IN SCOPE
Whether the requirement is going to be in the scope of the project. This will be agreed by the Company & SDU Team.
This Link Takes You to In Scope in the Template
TEST OR VERIFICATION
How the requirement will be checked and tested. For example, it can be based on a performance metric
This Link Takes You to Test of Verification in the Template
PHASE OR RELEASE
The project phase or date when the requirement will be delivered (Can be connected to the Gantt chart)
This Link Takes You to Phase or Release in the Template